## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
1 | 1 | US-001 | Implement candidate registration with webcam photo capture | MUST HAVE | No Dependency | Rohini Sai Kuchipudi | 3- Completed
1 | 1 | US-002 | Add live camera preview and manual Capture Photo / Retake option on registration | MUST HAVE | US-001 | Rohini Sai Kuchipudi | 3- Completed
1 | 1 | US-003 | Implement candidate login with credential verification | MUST HAVE | No Dependency | Rohini Sai Kuchipudi | 3- Completed
1 | 1 | US-004 | Implement exam session lifecycle: Not Started, In Progress, Paused, Submitted | MUST HAVE | US-003 | Rohini Sai Kuchipudi | 3- Completed
2 | 2 | US-005 | Build a shared camera manager to prevent webcam access conflicts | MUST HAVE | US-002 | Rohini Sai Kuchipudi | 3- Completed
2 | 2 | US-006 | Implement real-time face-presence detection using Haar Cascade classifier | MUST HAVE | US-005 | Rohini Sai Kuchipudi | 3- Completed
2 | 2 | US-007 | Stream candidate's live video feed to the exam page | SHOULD HAVE | US-005 | Rohini Sai Kuchipudi | 3- Completed
2 | 2 | US-008 | Detect browser tab switches and window focus loss using JavaScript | MUST HAVE | No Dependency | Rohini Sai Kuchipudi | 3- Completed
2 | 2 | US-009 | Log all monitoring events with timestamps to the database | MUST HAVE | US-006, US-008 | Rohini Sai Kuchipudi | 3- Completed
3 | 3 | US-010 | Design a weighted integrity scoring engine (0-100) | MUST HAVE | US-009 | Rohini Sai Kuchipudi | 3- Completed
3 | 3 | US-011 | Classify exam sessions into Low, Medium, or High risk bands | MUST HAVE | US-010 | Rohini Sai Kuchipudi | 3- Completed
3 | 3 | US-012 | Generate an AI-style natural-language summary report per candidate | SHOULD HAVE | US-010 | Rohini Sai Kuchipudi | 3- Completed
3 | 3 | US-013 | Build an analytics dashboard across all submitted sessions | SHOULD HAVE | US-010 | Rohini Sai Kuchipudi | 3- Completed
3 | 3 | US-014 | Implement K-Means clustering for behavioral grouping of candidates | COULD HAVE | US-009 | Rohini Sai Kuchipudi | 3- Completed
4 | 4 | US-015 | Capture an evidence screenshot at the moment of each flagged event | MUST HAVE | US-009 | Rohini Sai Kuchipudi | 3- Completed
4 | 4 | US-016 | Build an evidence gallery view per candidate session | SHOULD HAVE | US-015 | Rohini Sai Kuchipudi | 3- Completed
5 | 5 | US-017 | Build a consolidated, printable report per candidate | SHOULD HAVE | US-010, US-012, US-015 | Rohini Sai Kuchipudi | 3- Completed
5 | 5 | US-018 | Implement CSV and JSON export of all submitted sessions | COULD HAVE | US-013 | Rohini Sai Kuchipudi | 3- Completed
5 | 5 | US-019 | Implement real-time on-screen warning system during the exam | MUST HAVE | US-006, US-008 | Rohini Sai Kuchipudi | 3- Completed
5 | 5 | US-020 | Implement invigilator login and role-based access control | MUST HAVE | US-013 | Rohini Sai Kuchipudi | 3- Completed

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5
US-001 | 1 | Design database schema and build Flask registration route | 28-Jul-2026 | 29-Jul-2026 | Rohini Sai Kuchipudi | Design | 3- Completed | 6 | 4 | 0 | 0 | 0 | 0
US-001 | 2 | Implement OpenCV webcam photo capture on registration | 29-Jul-2026 | 30-Jul-2026 | Rohini Sai Kuchipudi | Coding | 3- Completed | 5 | 4 | 1 | 0 | 0 | 0
US-002 | 3 | Add live camera preview and Capture Photo / Retake button | 30-Jul-2026 | 31-Jul-2026 | Rohini Sai Kuchipudi | Coding | 3- Completed | 4 | 3 | 1 | 0 | 0 | 0
US-003 | 4 | Implement candidate login with credential check | 30-Jul-2026 | 30-Jul-2026 | Rohini Sai Kuchipudi | Coding | 3- Completed | 3 | 2 | 0 | 0 | 0 | 0
US-004 | 5 | Implement exam session status lifecycle in database | 31-Jul-2026 | 31-Jul-2026 | Rohini Sai Kuchipudi | Coding | 3- Completed | 4 | 3 | 1 | 0 | 0 | 0
US-005 | 6 | Build shared camera_manager module for single webcam access | 03-Aug-2026 | 03-Aug-2026 | Rohini Sai Kuchipudi | Build | 3- Completed | 5 | 4 | 1 | 0 | 0 | 0
US-006 | 7 | Integrate Haar Cascade face detection in background thread | 03-Aug-2026 | 04-Aug-2026 | Rohini Sai Kuchipudi | Coding | 3- Completed | 6 | 5 | 2 | 0 | 0 | 0
US-007 | 8 | Stream live video feed to exam page via MJPEG response | 04-Aug-2026 | 04-Aug-2026 | Rohini Sai Kuchipudi | Coding | 3- Completed | 4 | 3 | 1 | 0 | 0 | 0
US-008 | 9 | Implement JavaScript tab-switch and focus-loss detection | 04-Aug-2026 | 05-Aug-2026 | Rohini Sai Kuchipudi | Coding | 3- Completed | 3 | 2 | 0 | 0 | 0 | 0
US-009 | 10 | Build event logging API endpoint and database integration | 05-Aug-2026 | 05-Aug-2026 | Rohini Sai Kuchipudi | Coding | 3- Completed | 4 | 3 | 1 | 0 | 0 | 0
US-010 | 11 | Design and implement weighted integrity scoring formula | 11-Aug-2026 | 11-Aug-2026 | Rohini Sai Kuchipudi | Design | 3- Completed | 4 | 3 | 1 | 0 | 0 | 0
US-011 | 12 | Implement Low/Medium/High risk classification logic | 11-Aug-2026 | 12-Aug-2026 | Rohini Sai Kuchipudi | Coding | 3- Completed | 2 | 1 | 0 | 0 | 0 | 0
US-012 | 13 | Build rule-based natural-language report generator | 12-Aug-2026 | 12-Aug-2026 | Rohini Sai Kuchipudi | Coding | 3- Completed | 5 | 4 | 1 | 0 | 0 | 0
US-013 | 14 | Build analytics dashboard listing all submitted sessions | 13-Aug-2026 | 13-Aug-2026 | Rohini Sai Kuchipudi | Coding | 3- Completed | 5 | 4 | 1 | 0 | 0 | 0
US-014 | 15 | Implement K-Means clustering module for candidate behavior | 15-Aug-2026 | 15-Aug-2026 | Rohini Sai Kuchipudi | Coding | 3- Completed | 6 | 5 | 2 | 0 | 0 | 0
US-015 | 16 | Capture evidence screenshot on tab-switch / focus-loss events | 18-Aug-2026 | 19-Aug-2026 | Rohini Sai Kuchipudi | Coding | 3- Completed | 5 | 4 | 1 | 0 | 0 | 0
US-016 | 17 | Build evidence gallery page per candidate session | 19-Aug-2026 | 19-Aug-2026 | Rohini Sai Kuchipudi | Coding | 3- Completed | 3 | 2 | 0 | 0 | 0 | 0
US-017 | 18 | Build consolidated printable report page (score, report, evidence, cluster) | 01-Sep-2026 | 02-Sep-2026 | Rohini Sai Kuchipudi | Coding | 3- Completed | 6 | 5 | 2 | 0 | 0 | 0
US-018 | 19 | Implement CSV and JSON export routes | 02-Sep-2026 | 02-Sep-2026 | Rohini Sai Kuchipudi | Coding | 3- Completed | 3 | 2 | 0 | 0 | 0 | 0
US-019 | 20 | Build real-time warning toasts and face-absence banner with polling | 10-Sep-2026 | 10-Sep-2026 | Rohini Sai Kuchipudi | Coding | 3- Completed | 6 | 5 | 2 | 0 | 0 | 0
US-020 | 21 | Implement invigilator login, session-based access control, ownership checks | 15-Sep-2026 | 15-Sep-2026 | Rohini Sai Kuchipudi | Coding | 3- Completed | 5 | 4 | 1 | 0 | 0 | 0
US-017 | 22 | Write unit test plan, defect tracker, and Agile documentation | 16-Sep-2026 | 18-Sep-2026 | Rohini Sai Kuchipudi | System Test | 3- Completed | 8 | 6 | 3 | 1 | 0 | 0

## Stand up Meeting
Sprint Day | Impediments | Action Taken
Sprint 1 Day 2 | Captured registration photo appeared completely black due to the webcam not adjusting to lighting in time | Added a warm-up loop reading several frames before saving the photo, resolving the exposure issue
Sprint 1 Day 3 | Manual file replacement across multiple downloads caused confusion, with files landing in the wrong folder | Consolidated the project into a single permanent folder and standardised the file-replacement workflow
Sprint 2 Day 2 | OpenCV's CascadeClassifier failed with an AttributeError after a newer library version was auto-installed | Downgraded and pinned opencv-python to a known-compatible version in requirements.txt
Sprint 2 Day 3 | Face-absent time was always recorded as 0 seconds, later traced to the browser and backend both trying to access the webcam at once | Built a shared camera_manager module so only one process ever holds the camera
Sprint 2 Day 3 | Live video preview appeared broken because Flask's development server blocked on the continuous video stream | Enabled threaded mode in the Flask server so other requests are handled concurrently
Sprint 3 Day 5 | Older exam sessions submitted before the scoring feature existed showed no score in analytics | Wrote a one-time backfill script to retroactively compute scores for existing sessions
Sprint 4 Day 2 | Deciding when to trigger an evidence screenshot without capturing excessive images | Limited evidence capture to the exact moment of a tab-switch or focus-loss event only
Sprint 5 Day 3 | Analytics, clustering, and report pages had no access restriction and were viewable by anyone with the link | Introduced a separate invigilator login with session-based access checks and per-candidate ownership rules

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date
1 | Sprint 1 | 28-Jul-2026 | 01-Aug-2026
2 | Sprint 2 | 03-Aug-2026 | 08-Aug-2026
3 | Sprint 3 | 11-Aug-2026 | 15-Aug-2026
4 | Sprint 4 | 18-Aug-2026 | 22-Aug-2026
5 | Sprint 5 | 25-Aug-2026 | 18-Sep-2026
Team member name
Rohini Sai Kuchipudi
Start Doing | Stop Doing | Continue Doing | Action taken
Testing each module end-to-end immediately after building it | Manually editing code by pasting partial snippets into existing files | Verifying every fix with a real webcam test before moving on | Switched to always sending complete replacement files instead of partial edits, avoiding indentation errors
Reviewing the whole system for security gaps before final submission | Assuming a feature is 'done' once it visually works | Writing down every bug and its fix as it happens | Added an invigilator login after identifying that result pages had no access control
Keeping one single project folder for the whole internship | Creating a new folder or zip for every milestone update | Documenting design decisions directly in code comments | Consolidated all milestone files into one permanent folder with individual file replacements