## Defects
SI No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed)
1 | Rohini Sai Kuchipudi | 30-Jul-2026 | Registration photo captured via webcam appears completely black/dark | Sprint 1 | Rohini Sai Kuchipudi | Functional | Modified capture function to let the camera warm up for 30 frames before saving, resolving the exposure issue | 30-Jul-2026 | Closed
2 | Rohini Sai Kuchipudi | 30-Jul-2026 | Python IndentationError raised in app.py after a manual code edit to the photo capture function | Sprint 1 | Rohini Sai Kuchipudi | Environment/Setup | Replaced the entire function block with corrected indentation and verified syntax using py_compile | 30-Jul-2026 | Closed
3 | Rohini Sai Kuchipudi | 31-Jul-2026 | Registration photo preview continued showing live video instead of freezing on the captured photo | Sprint 1 | Rohini Sai Kuchipudi | UI/UX | Updated the capture button logic to switch the preview image source to the saved photo file, with a Retake option to return to live view | 31-Jul-2026 | Closed
4 | Rohini Sai Kuchipudi | 03-Aug-2026 | AttributeError: module 'cv2' has no attribute 'CascadeClassifier' on a newer OpenCV version installed by pip | Sprint 2 | Rohini Sai Kuchipudi | Environment/Setup | Downgraded opencv-python to version 4.10.0.84 and pinned the version in requirements.txt | 03-Aug-2026 | Closed
5 | Rohini Sai Kuchipudi | 03-Aug-2026 | Total face-absent time recorded as 0 seconds despite the candidate leaving the camera frame, caused by the browser and backend both trying to access the webcam separately | Sprint 2 | Rohini Sai Kuchipudi | Functional | Built a shared camera_manager module as a single access point, used by both the live video stream and the face-detection thread | 03-Aug-2026 | Closed
6 | Rohini Sai Kuchipudi | 03-Aug-2026 | Live video preview displayed as a broken or tiny icon on the exam page | Sprint 2 | Rohini Sai Kuchipudi | Performance | Enabled threaded mode in the Flask server so the continuous video stream connection does not block other page requests | 03-Aug-2026 | Closed
7 | Rohini Sai Kuchipudi | 15-Aug-2026 | Analytics table displayed 'None/100' for exam sessions submitted before the scoring feature was implemented | Sprint 3 | Rohini Sai Kuchipudi | Functional | Wrote a one-time backfill utility script to retroactively compute and store integrity scores for existing sessions | 15-Aug-2026 | Closed
8 | Rohini Sai Kuchipudi | 15-Sep-2026 | Analytics, clustering, and candidate report pages were accessible to anyone with the link, with no access restriction | Sprint 5 | Rohini Sai Kuchipudi | Security | Implemented a separate invigilator login with access-control checks, so only invigilators or the owning candidate can view result pages | 15-Sep-2026 | Closed
9 | Rohini Sai Kuchipudi | 17-Sep-2026 | Candidate passwords were stored in plain text, and invigilator credentials were hardcoded in the database with a default password, unsafe for a public GitHub repository | Sprint 5 | Rohini Sai Kuchipudi | Security | Implemented password hashing for candidate accounts using Werkzeug, and moved invigilator credentials to a local .env file excluded from Git via .gitignore | 17-Sep-2026 | Closed

## Sheet2
Type Of Defect options used: Functional, UI/UX, Performance, Environment/Setup, Security